## Planning template
One-term AI education plan
How to use: fill the blank table below with this term's two pilot activities, then give each one an owner, dates and review evidence. The second sheet is a completed fictional school example to compare against. The review-evidence column matters most — if you cannot say what you will look at afterwards, the activity cannot be reviewed.
Pilot activity | Owner | Dates / week | Review evidence (what to look at afterwards)
Leader's checklist — tick each item to confirm the plan is executable
Check item | Done?
Two pilot activities chosen, achievable within one term
Every activity has an owner (a named person or post)
Every activity has a date or week
Every activity states its review evidence — what to look at afterwards
Each activity can be tied to a planning requirement or a learning progression in the official documents
Mid-term and end-of-term review meetings have dates and an agenda
It is confirmed who collects and keeps the evidence

## Completed example
Completed example (fictional school)
The plan below is for a fictional primary school over one term (about 12 weeks), shown for illustration only. The owner names and dates are fictional and do not refer to any real school or person.
Pilot activity | Owner | Dates / week | Review evidence (what to look at afterwards)
1. Whole-school staff consensus workshop: understand the AI literacy framework and the school's direction | Ms Chan, curriculum coordinator | Week 2 (90 min) | Attendance record, post-session questionnaire, a first draft of the school's AI-use agreement
2. Cross-subject pilot lesson: one P5 General Studies period on checking an AI answer | Mr Lee, General Studies panel head, with the P5 teachers | Weeks 5-7 (one period per class) | Three anonymised pupil worksheet samples + a panel review note
3. Mid-term and end-of-term review | Ms Chan, curriculum coordinator | Weeks 6 and 12 | Evidence folder + a decision on next term's scope
The key judgement: the review-evidence column is what matters. If you cannot say what we will look at afterwards, the activity cannot be reviewed, which means it has not really been planned.
If you have any comments or questions about this resource, please email enquiry@beets-ai.com